## UCs Time and FPs
Finished Player Ucs | Time spent/planned | Function Points | Finished Graphical Use Cases | FPs | time spent/planned
Movement | 5 |  | Create Environment 1 | 42 | 6
Use Ability | 3.5 |  | Create Environment 2 | 60 | 8
FinishLevel | 13 |  | Create Environment 3 | 70 | 8
Start Game | 1.75 |  | Zones 2.0 | 94 | 10
End Game | 1.75 |  | Update Environment 1 | 58.8 | 5
Respawn | 4.5 |  | Update Environment 2 | 39.2 | 4
Main Menu | 8.75
Camera | 7 |  | Planned Graphical Use Cases
Planned Player Ucs |  |  | Many Graphical improvements | 165 | 16.9758
|  |  | Animations | 360 | 35.9298
Free Soul (Coding only) |  |  | Living surrounding | 273 | 27.4734
Gain Ability (Coding only)
Open Menu
Close Menu
Change Volume

## Graphical Calculation
scale
Number of needed particle systems | 6 | 10 FPs per PS
Complexity of the needed Models | 7 | Range from 1 (simple) to 10 (really complex)
Size of model | 5 | Range from 1 (small) to 5 (base Block Style)
Detail of model | 10 | Range from 1 (just a square) to 10 (super detailed but low poly style)
Influence on the Game | 3 | Estimated importance of the model / animation from 1 (just decor) to 10 (main character)
FPs: | 165